## Sheet1
Task ID | Task Description | Owner | Start Date | End Date | Status
1 | Restore WideWorldImporters database | Each member | 2025-09-23 | 2025-09-24 | Complete
2 | Draft 10 propositions + SQL queries | Each member | 2025-09-23 | 2025-09-24 | Complete
3 | Test queries in WideWorldImporters DB | Each member | 2025-09-24 | 2025-09-24 | Complete
4 | Record individual walkthrough MP4s | Each member | 2025-09-24 | 2025-09-26 | Complete
5 | Create group to-do list + Gantt chart | Wayne | 2025-09-25 | 2025-09-26 | Complete
6 | Consolidate all notebooks (.ipynb) | Wayne | 2025-09-26 | 2025-09-26 | Complete
7 | Consolidate all videos (.mp4) | Wayne | 2025-09-26 | 2025-09-26 | Complete
8 | Organize repo (Notebooks, Videos, Docs) | Wayne | 2025-09-26 | 2025-09-26 | Complete
9 | Zip repo contents for submission | Wayne | 2025-09-26 | 2025-09-26 | Complete
10 | Submit GitHub + ZIP links | Wayne | 2025-09-26 | 2025-09-26 | Complete